## Sheet1
Quarter | Fall Quarter | [5 empty] | Winter Quarter | [5 empty] | Spring Quarter
Week(s) | 1 and 2 | 3 and 4 | 5 and 6 | 7 and 8 | 9 and on | Winter Break | 1 and 2 | 3 and 4 | 5 and 6 | 7 and 8 | 9 and on | Spring Break | 1 and 2 | 3 and 4 | 5 and 6 | 7 and 8 | 9 and on
Requirements
Requirements Gathering
Check In With Customer
Design
Designing Architecture
Researching Music Providers
Developing Conceptual Model
Implementation
Making User Interface
Coding Class Heirarchy
Coding Authentication Methods
Coding Playback Feature
Implementing Access to Music Providers
Testing
Testing Usability (Alpha)
Testing Browser Compadibility
Mobile Device Testing
Requirements Testing
Testing Usability (Beta)
Documentation
Problem Statement
Design Document
Primary Presentation
Final Presentation
Final Document
Team Member Legend
Alexander Polatnick
Kristen Ronhovde
Sara Cassella
All Members